## SUMMARY
SUMMARY OF LOANS
Loans | Mobile | WEB | Comment
Salary Based Loan - WEMA Account | Passed | Passed
Salary Loan Liquidation | Passed | Passed
Salary Based Loan – Other banks | Passed | Passed
Salary Based Loan - Other employer with message | Passed | Passed
Salary Based Loan - My Bank Statement | Passed | Passed
Goal based Loan application | Passed | Passed
Goal based Loan top up | Passed | Passed
Goal based Loan Part payment | Passed | Passed
Goal based Loan Full repayment | Passed | Passed
Goal-cashout- goal-based loan -liquidation | Passed | Passed
Email notifications for loan activities | Passed | Passed
Device Loan - WEMA account | Passed | Passed
Device Loan - other banks account (Mobile) | Passed | Passed | Got to repayment screen for mandate set up
Device Loan - My Bank Statement | Passed | Passed
Payday Loan - WEMA | Passed | NA
Payday Loan - Other Bank | Passed | NA
Payday Loan - My Bank Statement | Passed | NA
Payday Loan Liquidation | Passed | NA
Pre-Qualified Payday loan - WEMA | Passed | Passed
Pre-Qualified Liquidation | Passed | Passed
Loan onboarding | Passed | NA

## Salary Based Loan
Web Test Summary
[6 empty] | Pass (P) | 93 | 98.94%
Created by |  | MUMIN OLABIYI |  |  |  | Fail (F) | 1 | 1.064%
Reviewed by |  | MICHAEL ADINEBO |  |  |  | Not Executed (NE) | 0 | 0%
Date | [5 empty] | Total | 94 | 100%
TC NO | TC ID | Test Title | Test Scenario | Test Execution Steps | Expected Result | Actual Result | Status | Comments | Date Tested | Tester | Developer
1 |  |  | Verify user is able to login to the app | - Login to app with valid e-mail and password | User should get logged in successfully | As Expected | P
2 |  | LOGIN | Verify user is unable to log in with invalid credentials | - Login to app with invalid e-mail and password | User should get Invalid Credentials as Error message | As Expected | P
3 |  |  |  | - Login to app with invalid e-mail and valid password | User should get Invalid Password as error message | As Expected | P
4 |  |  |  | - Login to app with empty e-mail and valid password | User should get Invalid E-mail enter as error message | As Expected | P
5 |  |  |  | - Login to app with valid e-mail and invalid password | User should get error message to enter Valid Password | As Expected | P
6 |  |  |  | - Login to app with invalid e-mail and empty password | User should get error message to enter Valid Credential | As Expected | P
7 |  |  |  | - Login to app with valid e-mail and empty password | User should get an error message to Enter Password | As Expected | P
8 |  |  | Verify if the data in password fied is visible or asterik | - Login to app with e-mail and password | User should see the password entered as asterik | As Expected | P
9 |  |  | Verify the Forget Password button Functionality | - Click on Forget Password on the Login Page | User shoud be able to reset Password | As Expected | P
10 |  |  | Verify if user log in with new password changed using Forget Password | - Login to app with valid e-mail and new password changed | User shoud be able to Log on with the new password and valid mail | As Expected | P
11 |  |  | Verify if user log in with old password while Password changed already effected | - Login to app with valid e-mail and old password | User should get error message to Enter Valid Password | As Expected | P
12 |  | LOAN DASHBOARD | Verify user is able to click on LOANS in the menu on the bottom | - Login to App - Click on Loans Tab | User should be taken to the loan dashboard | As Expected | P
13 |  |  | Verify user clicks and hold the LOANS in the menu on the bottom | - Login to App - Click and hold on Loans Tab | User should remain on the dashboard | As Expected | P
14 |  |  | Verify user double click the LOANS in the menu on the bottom | - Login to App - Doubleclick on Loans Tab | User should be taken to the loan dashboard | As Expected | P
15 |  |  | Verify user is able to click on LOANS in Edit Favourites if present | - Login to App - Click on Loans Tab | User should be taken to the loan dashboard | As Expected | P
16 |  |  | Verify user clicks and hold the LOANS in Edit Favourites if present | - Login to App - Click and hold on Loans Tab | User should remain on the dashboard | Not As Expected | F
17 |  |  | Verify user double click the LOANS in Edit Favourites if present | - Login to App - Doubleclick on Loans Tab | User should be taken to the loan dashboard | As Expected
18 |  | LOAN REQUEST INITIATION - EXISTING CUSTOMER | Verify user is able to click on TAKE A LOAN on the loan dashboard | - Login to app - click on LOANS - click on TAKE A LOAN | User should be taken to the list of loan options after clicking on TAKE A LOAN | As Expected | P
19 |  |  | Verify user is able to see all the LOANS options available | - Login to app - click on LOANS | User should be able to see the list of loan options available | As Expected | P
20 |  |  | Verify user is able to click on SALARY BASED LOANS in the options and is taken to the loan details page | - Login to app - click on LOANS - click on TAKE A LOAN - click on SALARY BASED LOANS | User should be taken to the Salary Based Loan page after clicking on button | As Expected | P
21 |  |  | Verify user is able to select Yes or No with dropdown arrow. Yes for wema bank customer or No for non Wema bank customer | - Login to app - click on LOANS - click on TAKE A LOAN - click on SALARY BASED LOANS - Click the drop down arrow to select Yes or No | User should be able to select either Yes or No | As Expected | P
22 |  |  | Verify Loan Calculator is visible on the Salary Based Lending Screen | - click on LOANS - click on TAKE A LOAN - click on SALARY BASED LOAN | Loan Calculator is visible | As Expected | P
23 |  |  | Verify user is able to Enter loan Amount | - click on LOANS - click on TAKE A LOAN - click on SALARY BASED LOAN - Click the drop down arrow to select Yes or No - Enter Loan Amount | User should be able to enter a valid Amount | As Expected | P
24 |  |  | Verify User can slide and click on Tenor between 0 to 24 Months | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the drop down arrow to select Yes or No - Enter Amount - Slide left or right to pick Tenor | User should be able to select tenor | As Expected | P
25 |  |  | Verify User is not able to Proceed if the Tenor Month selected is 0 | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the drop down arrow to select Yes or No - Enter Amount - Click and slide on tenor - Ensure Selected tenor is 0 Month | Repayment tenor can not be less than a month | As Expected | P
26 |  |  | Verify user is not able to proceed if loan amount is negative | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the drop down arrow to select Yes or No - Enter Negative Amount | Loan amount cannot be in Negative value | As Expected | P
27 |  |  | Verify user is not able to proceed if loan amount is ZERO | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the drop down arrow to select Yes or No - Enter ZERO Amount - Slide left or right to pick Tenor | Loan amount cannot be Zero | As Expected | P
28 |  |  | Verify Estimated Monthly repayment is visible based on Loan Amount Entered | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the drop down arrow to select Yes or No - Enter Amount - Slide left or right to pick Tenor | Estimated monthly repayment and applicable interest rate should be seen | As Expected | P
29 |  |  | Verify the Amount Entered is not less than 5,000 and not greater than 4,000,000 | - Click on TAKE A LOAN - Click on Salary Based Loan - Enter Amount (5,000≥amount≤4,000,000) | Minimum Amount is 5,000 and Maximum is 4,000,000 | As Expected | P
30 |  |  | Verify Estimated Monthly repayment is rounded down to Thousands | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the drop down arrow to select Yes or No - Enter Amount - Slide left or right to pick Tenor - Confirm that Estimated Monthly Repayment is rounded down to Thousands | Estimated monthly repayment and applicable interest rate should be seen - Amount is rounded to thousands | As Expected | P
31 |  |  | Verify user is able to validate Estimated amount | - Click on TAKE A LOAN - Click on Salary Based Loan - Enter Amount - Slide left or right to pick Tenor | Repayment amount should be calculated correctly | As Expected | P
32 |  |  | Verify the user is able to validate Estimated amount if the Amount is Altered | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the drop down arrow to select Yes or No - Enter Amount - Slide left or right to pick Tenor - Alter Amount Entered | Repayment amount should be calculated correctly | As Expected | P
33 |  |  | Verify If Loan process can proceed | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the drop down arrow to select Yes or No - Enter Amount - Slide left or right to pick Tenor - Click on Proceed | Loan process should proceed to Employer Details | As Expected | P
34 |  | LOAN REQUEST INITIATION - EMPLOYER DETAILS | Verify that Users can select Industry from dropdown list | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the drop down arrow to select Yes or No - Enter Amount - Slide left or right to pick Tenor - Click on GET STARTED - Click on Industry Dropdown list - Select Industry of choice | Industry is selected | As Expected | P
35 |  |  | Verify that Users can select Employer from dopdown list | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the drop down arrow to select Yes or No - Enter Amount - Slide left or right to pick Tenor - Click on GET STARTED - Click on Employer Dropdown list - Select Employer of choice | Employer is selected | As Expected | P
36 |  |  | Verify User can Upload WorkID Front and Back | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the drop down arrow to select Yes or No - Enter Amount - Slide left or right to pick Tenor - Click on GET STARTED - Click on Industry Dropdown list - Select Industry of choice - Select Employer - Click on WorkID - Add Photo/Take Photo/Choose from Gallery | Work ID is Captured successfully | As Expected | P
37 |  |  | Verify User cannot proceed by Capturing workID alone | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the drop down arrow to select Yes or No - Enter Amount - Slide left or right to pick Tenor - Click on Proceed - Click on WorkID - Add Photo/Take Photo/Choose from Gallery | Pop -up message displayed shows - You need to select your employer's Industry - You need to select your employer's name | As Expected | P
38 |  | ACCOUNT DETAILS PAGE WEMA ACCOUNT | Verify Loan has Incomplete Status on Loan DashBoard | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the drop down arrow to select Yes or No - Enter Amount - Slide left or right to pick Tenor - Click on GET STARTED - Click on Industry Dropdown list - Select Industry of choice - Select Employer - Click on WorkID - Add Photo/Take Photo/Choose from Gallery - Click back to Dashboard Button | User should be redirected to the Loan DashBoard page with status Discard and Proceed | As Expected | P
39 |  |  | Verify User can Proceed an Incomplete Loan setup | - Click on Loans from DashBoard - Click on Proceed | User should be directed to Employer Details page | As Expected | P
40 |  |  | Verify User can Discard an Incomplete Loan setup | - Click on Loans from DashBoard - Click on Discard - Click on Proceed | User should see Pop-Up message stating "Are you sure you want to discard your current loan application ? Loan is successfully dismissed | As Expected | P
41 |  |  | Verify user is able to select WEMA ACCT to debit | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the drop down arrow to select Yes or No - Enter Amount - Slide left or right to pick Tenor - Click on GET STARTED - Click on Industry Dropdown list - Select Industry of choice - Select Employer - Click on WorkID - Add Photo/Take Photo/Choose from Gallery - Click on Proceed | User should see "On what account do you want this loan to be charged" | As Expected | P
42 |  |  | Verify user is able to slide between different accounts if he has more than one account saved on the profile | - Select Account to Debit from list of Accounts | User should be able to slide between accounts | As Expected | P
43 |  |  | Verify the terms of consent is displayed with a text box on each of the page, and user is unable to proceed without selecting check box | - Click on Check Box | User should be able to check box and should not be able to proceed if box is unchecked | As Expected | P
44 |  | ACCOUNT DETAILS PAGE OTHER ACCOUNT | Verify user is able to Proceed Loan Application | - Select Account to Debit from list of Accounts - Click on Check Box - Click on Proceed Button - Click on Confirm Button | User is redirected to MORE DETAILS PAGE "On the premesis of having 6 month Accounting Entries" | As Expected | P
45 |  |  | Less than 6 Month Accounting Entries Verify User is redirected to Upload Bank Statement | - Click on Proceed Button - Click on Upload - Select file to upload | User should be able to upload bank statement | As Expected | P | Upload statement is currently suspended AND REPLACE BY myBankStatement
46 |  |  | Verify user is able to select My OTHER ACCT | - Click on TAKE A LOAN - Click on Salary Based Loan - Enter Amount - Slide left or right to pick Tenor - Click on GET STARTED - Click on Industry Dropdown list - Select Industry of choice - Select Employer - Click on WorkID - Add Photo/Take Photo/Choose from Gallery - Click on Proceed - Click on My Other Bank Account | User should see "On what account do you want this loan to be charged" | As Expected | P
47 |  |  | Verify User should able to enter Amount | - Enter a valid Account Number | Account Number is not Validated at this point in the loan process | As Expected | P
48 |  | eSTATEMENT VERIFICATION PAGE | Verify User can select Bank from Drop down option | - Click on Drop Down Option - Select Bank | Bank is selected from list of available banks | As Expected | P
49 |  |  | Verify User can click on terms Check Box | - Click on Check Box | Check Box is Clicked successfully | As Expected | P
50 |  |  | Verify User can click on Proceed Button | - Click on Proceed Button - Click on proceed to confirm that the input is correct | User is redirected to eStatement Verification Page | As Expected | P
51 |  |  | Verify user is able to see "Kindly enter ticket number and password sent to you via sms to confirm that you're the owner of the provided account" | - Click on Proceed | User should be able to click on PROCEED button to continue application | As Expected | P
52 |  | DOCUMENT UPLOAD PAGE | Verify User should see the following details on Ticket Number Password Proceed Button | - Click on LOANS | User should see the info of the listed | As Expected | P
53 |  |  | Verify User can enter Ticket Number and Password | - Enter ticket number and Password | User should be able to enter ticket number | As Expected | P
54 |  | MORE DETAILS PAGE | Verify User can click on Proceed Button | - Click on Proceed Button - Click on proceed to confirm that the input is correct | User is redirected to Document Upload | As Expected | P
55 |  |  | Verify User is able to upload Bank account statement | - Click on Upload Button - Upload statement | Statement is uploaded successful "Your statement has been successfully uploaded and will be reviewed within 24 hours. You will see your progress status on your dashboard" | As Expected | P
56 |  |  | Verify User is able to click on Continue button | - Click on Continue Button | User is redirected to Loan Dashboard | As Expected | P
57 |  |  | Verify User is able to enter Educational Qualification from Drop Down list | - Click Drop down List and Select option | Option is selected successfully | As Expected | P
58 |  |  | Verify User is able to enter Number of Dependents from Drop Down List | - Click Drop down List and Select option | Option is selected successfully | As Expected | P
59 |  |  | Verify User is able to enter Number of years of experience in Job from Drop Down list | - Click Drop down List and Select option | Option is selected successfully | As Expected | P
60 |  | SCORE CARD RESULT | Verify User can click on Back to Dashboard Button | - Click on Back to Dashboard Button | User is redirected to Loan Dashboard | As Expected | P
61 |  |  | Verify User is able to proceed on Loan Dashboard | - Click on Proceed Button on loan Dashboard - Click on Accept Button | - User is redirected to Score Card Result |  | P
62 | [6 empty] | P
63 |  |  | Verify user is able to see " Hi John Congratulations!!! Your loan has been granted. View details below." | - Click on Proceed on Loan DashBoard | Text is visible | As Expected | P
64 |  |  | Verify user is able to see Loan Amount Tenor (months) Monthly Repayment | - Click on Proceed on Loan DashBoard | Text is visible | As Expected | P
65 |  | TERMS | Verify Accept Button is clickable | - Click on Accept Button- | User is redirected to Terms Page | As Expected | P
66 |  |  | Verify Decline Button is clickable | - Click on Decline Button - Click on Proceed to reject the loan | Loan is terminated | As Expected | P
|  | LOAN EligibilityCheckID |  |  |  |  | P
67 |  |  | Verify User can click on Check Box "I agree with Loans Terms & Conditions." | - Click on Proceed Button | User is redirected to Loan DashBoard "Incomplete Salary Based Lending Setup" | As Expected | P
|  |  | Verify EligibilityCheckID column is NULL on Digital Loan before ScoreCard is Run | - Check DigitalLoan Table to confirm EligibilityCheckID is not updated - Check Create and Disburse Loan Table to confirm Loan has NOT being Created | EligibilityCheckId value is NULL on Digital Loan Loan is not created on Loan Management - Create and Disburse Table | As Expected | P
68 |  |  | Verify EligibilityCheckID generated on ScoreCard tallies with Digital Loan and LoanManagement | - Check CreateAndDisburse Table to confirm EligibilityCheckID column - Check DigitalLoan Table to confirm EligibilityCheckID | Digital Loan and Create and disburse Table have same EligibilityCheckID | As Expected | P
69 |  |  | Update EligibilityCheckID generated on ScoreCard and ensure it DOES NOT tally with EligibilityCheckId in Digital Loan and LoanManagement | - Check ScoreCard Table to confirm EligibilityCheckId is updated - Check CreateAndDisburse Table to confirm EligibilityCheckID is not Updated - Check DigitalLoan Table to confirm EligibilityCheckID is not updated | Successfully generated loan account - Investigation reponse - Loan Eligibility failed! | As Expected | P
70 |  |  | Verify EligibilityCheckID generated on ScoreCard table does NOT exist before creation using an Existing USER | - Check the ScoreCard Table and validate EligibilityCheckId does not Exist previously | EligibilityCheckId is generated NEWLY and persisted on ScoreCard Table | As Expected | P
71 |  | Loan Amount Validation | Verify LoanId of LoanQualifications table is persisted on Create and Disburse Table - EligibilityCheckId Column is same | - Check the Create and Disburse Table -EligibilityCheckId Column and confirm the value is same with LoanId of LoanQualification table - Check the isPrequalified True | EligibilityCheckId equals to LoanId on Loan Qualifications Table - isPrequalified is True | As Expected | P
72 |  |  | Verify LoanId of LoanQualifications table is NOT persisted on Create and Disburse Table - EligibilityCheckId Column | - Process a pre-qualified Payday Loan - Update the LoanId on Loan Qualifications table - Check the Create and Disburse Table -EligibilityCheckId Column and confirm the value is NOT same with LoanId on Loan Qualification Table - Check the isPrequalified True | EligibilityCheckId equals to LoanId on Loan Qualifications Table - isPrequalified is True | As Expected | P
73
74 |  |  | Verify Loan Amount requested during Loan process is Disbursed | - Confirm on Create and Disburse Table Loan Amount is same during loan request | Loan Amount Disbursed is same amount with Amount requested | As Expected | P
75 |  | DISBURSEMENT | Verify Loan is not Disbursed when Loan Amount on DB is greater than amount requested on application (Salary Based Loan) | - Update the Loan amount on the create and disburse table to a greater amount than the loan amount requested. - Confirm on Create and Disburse Table that Loan is not Disbursed - Confirm on Create and Disburse Table the response during disbursement | Loan Disbursement status is False Equity contribution: 0.0 - Investigation reponse - Loan Eligibility failed! | As Expected | P
76 |  |  | Verify Loan is Disbursed when Loan Amount on DB is greater than amount requested on application and NOT greater than the Eligible PreQualified Amount on loan qualifications table (PreQualified Loan) | - Update the Loan amount on the create and disburse table to a greater amount than the loan amount requested. - Confirm on Create and Disburse Table that Loan is Disbursed - Confirm on Create and Disburse Table the response during disbursement | Loan Disbursement status is True Equity contribution: 0.0 - Finacle reponse - Charges was collected successfully - Finacle reponse - VAT fee was collected successfully | As Expected | P
77 |  |  | Verify Loan is Disbursed when Loan Amount on DB is greater than amount requested on application and greater than the Eligible PreQualified Amount on loan qualifications table (PreQualified Loan) | - Update the Loan amount on the create and disburse table to a greater amount than the loan amount requested and greater than the Eligible amount on loan qualification table - Confirm on Create and Disburse Table that Loan is NOT Disbursed - Confirm on Create and Disburse Table the response during disbursement | Loan Disbursement status is False Equity contribution: 0.0 - Investigation reponse - Loan Eligibility failed! | As Expected | P
78 |  |  | Verify that Loan is disbursed and account Credited with Loan Amount | Click on Home Button Click on Transaction History to confirm VAT, management & insurance fee is charged | Loan Amount is credited VAT, management & Insurance fee is charged accordingly. | As Expected | P
79 |  |  | Verify that Loan is disbursed and account Credited with Loan Amount | Click on Home Button Click on Transaction History to confirm Loan amount | Loan Amount is credited to user's account | As Expected | P
80 |  |  | Verify that User is notified by SMS and Mail on status, credit and debit of Loan | Check sms is received on credit of loan amount | SMS and Mail is received accordingly | As Expected | P
81 |  | LIQUIDATION | Verify User can Liquidate a Salary based Loan Amount | Click on Loans Button Swipe on Current Loan and select loan Click on Pay Off Loan Click on YES button to confirm | User is redirected to Loan Repayment | As Expected | P
82 |  |  | Verify User can see outstanding loan balance, accumulated Interest to be deducted | Select Account to Debit Enter ALAT PIN Click on PAY LOAN Button | User is displayed with a message "Your Salary based loan was successfully paid off" | As Expected | P
83 |  |  | Verify that User is notified by SMS and Mail on status, debit of Loan | Check sms and mail is received on debit of loan amount | SMS and Mail is received accordingly | As Expected | P
84
|  | INTEREST RATE REFACTOR | Verify Applicable Interest rate is display if User's account is domiciled with Wema bank and the tenor is 12 months on the loan calculator page | - Click on TAKE A LOAN - Click on Salary Based Loan - Select from dropdown to indicate Customer is Wema bank domiciled - Enter Amount - Slide left or right to pick Tenor = 12 months | User should be able to get the applicable interest rate of 2.08%p.m i.e @25%p.a | As Expected | P
85 |  |  | Verify Applicable Interest rate is display if User's account is domiciled with Wema bank and the tenor is less than 12 months on the calculator page | - Click on TAKE A LOAN - Click on Salary Based Loan - Select from dropdown to indicate Customer is Wema bank domiciled - Enter Amount - Slide left or right to pick Tenor lesser than 12 Months | User should be able to get the applicable interest rate of 2.08%p.m i.e @25%p.a | As Expected | P
86 |  |  | Verify Applicable Interest rate is display if User's account is domiciled with Wema bank and the tenor is more than 12 months on the calculator page | - Click on TAKE A LOAN - Click on Salary Based Loan - Select from dropdown to indicate Customer is Wema bank domiciled - Enter Amount - Slide left or right to pick Tenor greater than 12 Months | User should be able to get the applicable interest rate of 2.25%p.m i.e @27%p.a | As Expected | P
87 |  |  | Verify Applicable Interest rate is display if User's account is not domiciled with Wema bank and the tenor is 12 months on the loan calculator page | - Click on TAKE A LOAN - Click on Salary Based Loan - Select from dropdown to indicate Customer is Other bank domiciled - Enter Amount - Slide left or right to pick Tenor = 12 months | User should be able to get the applicable interest rate of 2.17%pm i.e @26%p.a | As Expected | P
88 |  |  | Verify Applicable Interest rate is display if User's account is not domiciled with Wema bank and the tenor is less than 12 months on the loan calculator page | - Click on TAKE A LOAN - Click on Salary Based Loan - Select from dropdown to indicate Customer is Other bank domiciled - Enter Amount - Slide left or right to pick Tenor lesser than 12 Months | User should be able to get the applicable interest rate of 2.17%pm i.e @26%p.a | As Expected | P
89 |  |  | Verify Applicable Interest rate is display if User's account is not domiciled with Wema bank and the tenor is more than 12 months on the loan calculator page | - Click on TAKE A LOAN - Click on Salary Based Loan - Select from dropdown to indicate Customer is Other bank domiciled - Enter Amount - Slide left or right to pick Tenor 12 Months greater | User should be able to get the applicable interest rate of 2.50%pm i.e @30%p.a | As Expected | P
90 |  |  | Verify Applicable Interest rate is changed when User's alter the option of account from Wema bank to other bank and the tenor is 12 months on the loan calculator page, | - Click on TAKE A LOAN - Click on Salary Based Loan - Select from dropdown to indicate Customer is Wema bank domiciled - Enter Amount - Slide left or right to pick Tenor 12 Months - Select from dropdown to indicate Customer is Other bank domiciled | User should be able to get the applicable interest rate to change from 2.08% to i.e 25%p.a 2.17%pm i.e @26%p.a | As Expected | P
91 |  |  | Verify Applicable Interest rate is changed when User's alter the option of account from other bank to Wema Bank and the tenor is less than 12 months on the loan calculator page, | - Click on TAKE A LOAN - Click on Salary Based Loan - Select from dropdown to indicate Customer is Other bank domiciled - Enter Amount - Slide left or right to pick Tenor 12 Months lesser - Select from dropdown to indicate Customer is Wema bank domiciled | User should be able to get the applicable interest rate to change from 2.17%pm i.e @26%p.a to 2.08% i.e @25% | As Expected | P
92 |  |  | Verify Applicable Interest rate is changed when User's alter the option of account from Wema bank to other bank and the tenor is more than 12 months on the loan calculator page, | - Click on TAKE A LOAN - Click on Salary Based Loan - Select from dropdown to indicate Customer is Wema bank domiciled - Enter Amount - Slide left or right to pick Tenor 12 Months greater - Select from dropdown by select NO to indicate Customer is Other bank domiciled | User should be able to get the applicable interest rate to change from 2.25% i.e@27% to 2.50%pm i.e @30%p.a | As Expected | P
93 |  |  | Verify debit account page is projected as WEMA if domicile account is Wema bank | - Click on TAKE A LOAN - Click on Salary Based Loan - Select from dropdown and select YES to indicate Customer is Wema bank domiciled - Enter Amount - - Slide left or right to pick Tenor - Click on Proceed | User debit account should project Wema bank | As Expected | P
94 |  |  | Verify debit account page is projected as Other Bank if domicile account is NOT Wema bank | - Click on TAKE A LOAN - Click on Salary Based Loan - Select from dropdown by select NO to indicate Customer is Other bank domiciled - Enter Amount - - Slide left or right to pick Tenor - Click on Proceed | User debit account should project Other bank | As Expected | P
95 |  |  | Verify Estimated amount changed when User's alter the amount on the loan calculation page | - Click on TAKE A LOAN - Click on Salary Based Loan - Select from dropdown by select NO to indicate Customer is Other bank domiciled - Enter Amount - - Slide left or right to pick Tenor - Alter the initial amount | Estimated Amount should be in accordance of the Amount entered | As Expected | P
|  |  | Verify user should not be able to Proceed if no Tenor is selected | - Click on TAKE A LOAN - Click on Salary Based Loan - Select from dropdown by select NO to indicate Customer is Other bank domiciled - Enter Amount - Click on Proceed | User should not be able to Proceed if no tenor (Month) is selected | As Expected
|  |  | Verify user is able to slide between different accounts if he has more than one account saved on the profile | - Select Account to Debit from list of Accounts | User should be able to slide between accounts "On what account do you want this loan to be charged" | As Expected
|  |  | Ensure the API fetch statement from Finacle if account is Wema bank | - Click on TAKE A LOAN - Click on Salary Based Loan - Click dropdown to select Yes - Enter Amount - Slide left or right to pick Tenor - Click on GET STARTED - Click on Industry Dropdown list - Select Industry of choice - Select Employer - Click on WorkID - Add Photo/Take Photo/Choose from Gallery - Click on Proceed | APIs should fecth the internal customer from Finacle |  | P
|  | . | Ensure the statement from Finacle is converted to PDF irrespective of the later format and send to backoffice for review | - Click on TAKE A LOAN - Click on Salary Based Loan - Click dropdown to select Yes - Enter Amount - Slide left or right to pick Tenor - Click on GET STARTED - Click on Industry Dropdown list - Select Industry of choice - Select Employer - Click on WorkID - Add Photo/Take Photo/Choose from Gallery - Click on Proceed | The statement of account get from Finacle should be converted to PDF and send to the backoffice for review and User's should get a message Loan application successful, your bank statement is being review. Kindly check back within 24hours |  | P
|  | myBankStatement | Verify User is able to select Other bank from the loan page | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the dropdown to select No | User should see "Is your account with wema bank" and NO | As Expected | P
|  |  | Verify user is able to select bank from the list of bank with the drop down arrow | - Click on TAKE A LOAN - Click on Salary Based Loan - Click the dropdown to select No - Enter Amount - Slide left or right to pick Tenor - Click on GET STARTED - Click on Industry Dropdown list - Select Industry of choice - Select Employer - Click on WorkID - Add Photo/Take Photo/Choose from Gallery - Click on Proceed - Click and select bank from list of banks | User's should be able to select bank from the list of bank | As Expected | P
|  |  | Verify user is able to enter valid account number | - Enter valid account number | User's should be able to enter valid account number | As Expected | P
|  |  | Verify user cannot proceed if entered wrong account number | - Enter invalid account number | User should get an error message "we observed a BVN mismatch, please input the correct account details" | As Expected | P
|  |  | Verify if user is able to enter valid phone number linked to the BVN/account | - Enter valid phone number | User's should be able to enter valid phone number | As Expected | P
|  |  | Verify if user can proceed if inputed the wrong phone number | - Enter wrong phone number | User should be able to see projected masked phone number request, to complete for validation | As Expected | P
|  |  | Verify user is able to enter valid alat pin | - Enter valid pin | User's should be enter valid pin and proceed | As Expected | P
|  |  | Verify if user could proceed if entered invalid PIN | - Enter Invalid pin | User should get an error message "You have inputted an invalid pin" | As Expected | P
|  |  | Verify the number of trial is subject to 3 for entering invalid pin . | - Enter Invalid pin twice | User's should get the message of trial remaning | As Expected | P
|  |  | Verify the loan process terminate automatically subject to entering invalid pin thrice | - Enter invalid pin thrice | User should get an error message "Loan process terminated due to wrong pin" | As Expected | p
|  |  | Verify user tick the consent box permitting access to my bank statement with other banks to determine my income eligibility. | - Click on Check Box | Check Box is Clicked successfully | As Expected | P
|  |  | Verify if User can click on Proceed Button with right account number, phone number and pin | - Enter valid account number, phone number and pin - Click on Proceed Button - Click on proceed | User should be able to proceed | As Expected | P
|  |  | Verify user cannot proceed if the consent box is not tick | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on proceed | User should not be able to proceed | As Expected | P
|  |  | Ensure NIP's endpoint was queried to get customer name enquiry and BVN | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on proceed | APIs should queried NIP's endpoint to get customer name enquiry and BVN | As Expected | P
|  |  | Ensure the BVN number returned is validated and matches with the customer BVN on Wema Bank DB | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on proceed | API's validate the fetched customer details from NIP's if matches with the Wema Bank DB | As Expected | P
|  |  | Ensure the CSWF API was called from my bank statement to get the customer statement of account to conclude the process | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on proceed | APIs should fetch account statement of the account from myBankStatement and send to the backoffice for review. and User's should be notified. | As Expected | P
|  | eSTATEMENT VERIFICATION PAGE | Verify User see progress message after click on proceed with valid data input | - Click on Proceed Button - Click on proceed to confirm that the input is correct | User should be able to see "We are currently fetching your statement of account, please give us a minute" | As Expected | P
|  |  | Verify if user get a response message after eSTATEMENT was generated successfully | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on Check Box - Click on proceed | The statement of account get from Finacle should be converted to PDF and send to the backoffice for review and User's should get a message "Loan application successful, your bank statement is being review. Kindly check back within 24hours" | As Expected | P
|  |  | Verify if user was directed to the loan dashboard after successful statement upload from finacle or any 3rd party service and converted to PDF | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on Check Box - Click on proceed | User should be able to get the message "Your statement has been uploaded and will be reviewed within 24hours". | As Expected | P
|  |  | Ensure customer loan was rejected if getting statement from finacle or any 3rd party fails | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on Check Box - Click on proceed | User should be able to get the message "Your request was declined because we are unable to validate your statement of account details due to service downtime, please try again later." | As Expected | P
|  |  | Ensure customer loan was rejected if getting statement from finacle or any 3rd party fails due to unavailability of required data | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on Check Box - Click on proceed | User should be able to get the message "Your request was declined because we are unable to get your statement of account details, please visit the nearest branch for more loan options" | As Expected | P
|  |  | Ensure existing parameters that apply is still maintain for the statement upload | - Login to the app - Click on Loan - Proceed with existing loan | User should be able to continue with the existing loan process if statement review was successful | As Expected | P

## Pre-Qualified Loan
Web Test Summary
[6 empty] | Pass (P) | 16 | 100%
Created by |  | MUMIN OLABIYI |  |  |  | Fail (F) | 0 | 0%
Reviewed by |  | MICHAEL ADINEBO |  |  |  | Not Executed (NE) | 0 | 0%
Date | [5 empty] | Total | 16 | 100%
TC NO | TC ID | Test Title | Test Scenario | Test Execution Steps | Expected Result | Actual Result | Status | Comments | Date Tested | Tester | Developer
1 |  | LOAN DASHBOARD | Verify user is able to login to the app | - Login to app with valid credentials | User should get logged in successfully | As Expected | P
2 |  |  | Verify user is able to click on LOANS in the menu on the bottom | - Login to App - Click on Loans Tab | User should be taken to the loan dashboard | As Expected | P
3 |  |  | Verify user is able to click on TAKE A LOAN on the loan dashboard | - Login to app - click on LOANS - click on TAKE A LOAN | User should be taken to the list of loan options after clicking on TAKE A LOAN | As Expected | P
4 |  |  | Verify user is able to see Pre-approved Loan Offer in the LOANS PAGE | - Login to app - click on LOANS - click on TAKE A LOAN - Click on Take This Loan | User should be able to see Pre-approved loan offer - User is redirected to Pre-approved Loan | As Expected | P
5 |  | PRE-APPROVED LOAN PAGE | Verify User can see Loan Details - Eligible Amount - Due Date - How much do you want to borrow - Repayment Amount - "Please note that 1.5% of the approved loan amount will be charged as management and Insurance fee." | - Enter Amount - Click on Proceed | User is redirected to Terms and Conditions | As Expected | P
6 |  |  | Verify User should not be able to Enter Less than 5,000 and not more than Ore-Approved Amount | - Enter Amount - Click on Proceed | User should be prompted to Valid Amount | As Expected | P
7 |  |  | Verify User should not be able to Enter Negative Amount | - Login to app - click on LOANS - click on TAKE A LOAN - Click on Take This Loan - Enter Negative Amount | Amount cannot be Negative | As Expected | P
8 |  |  | Verify User should not proceed if Enter ZERO (0) amount | - Login to app - click on LOANS - click on TAKE A LOAN - Click on Take This Loan - Enter Zero (0) Amount | User should be prompted to Enter Amount | As Expected | P
9 |  |  | Verify user is able to validate Estimated amount | - Click on TAKE A LOAN - Enter Amount - Slide left or right to pick Tenor | Repayment amount should be calculated correctly | As Expected | P
10 |  |  | Verify the loan calculated the right amount of Estimated payment if the Amount is Altered | - Click on TAKE A LOAN - Enter Amount - Slide left or right to pick Tenor - Alter Amount Entered | Repayment amount should be calculated correctly | As Expected | P
9 |  |  | Verify User can click on check Box to "I agree with Loans Terms and Conditions." | - Click on Proceed | User is redirected to Loan DashBoard | As Expected | P
12 |  | DISBURSEMENT | Verify that Loan is disbursed and account Credited with Loan Amount | Click on Home Button Click on Transaction History to confirm VAT, management & insurance fee is charged | Loan Amount is credited VAT, management & Insurance fee is charged accordingly. | As Expected | P
13 |  |  | Verify that User is notified by SMS and Mail on status, credit and debit of Loan | Check sms is received on debit of charges Check sms is received on credit of loan amount | SMS is received | As Expected | P
14 |  | LIQUIDATION | Verify User can Liquidate a Payday Loan Amount | Click on Loans Button Swipe on Current Loan and select loan Click on Pay Off Loan Click on YES button to confirm | User is redirected to Loan Repayment | As Expected | P
15 |  |  | Verify User can see outstanding loan balance, accumulated Interest to be deducted | Select Account to Debit Enter ALAT PIN Click on PAY LOAN Button | User is displayed with a message "Your pay day loan was successfully paid off" | As Expected | P
16 |  |  | Verify that User is notified by SMS and Mail on status, debit of Loan | Check sms and mail is received on debit of loan amount | SMS and Mail is received accordingly | As Expected | P

## PayDay Loan
Web Test Summary
[6 empty] | Pass (P) | 28 | 100%
Created by |  | MUMIN OLABIYI |  |  |  | Fail (F) | 0 | 0%
Reviewed by |  | MICHAEL ADINEBO |  |  |  | Not Executed (NE) | 0 | 0%
Date | [5 empty] | Total | 28 | 100%
TC NO | TC ID | Test Title | Test Scenario | Test Execution Steps | Expected Result | Actual Result | Status | Comments | Date Tested | Tester | Developer
1 |  | LOAN DASHBOARD | Verify user is able to login to the app | - Login to app with valid credentials | User should get logged in successfully | As Expected | P
2 |  |  | Verify user is able to click on LOANS in the menu on the bottom | - Login to App - Click on Loans Tab | User should be taken to the loan dashboard | As Expected | P
3 |  |  | Verify user is able to click on TAKE A LOAN on the loan dashboard | - Login to app - click on LOANS - click on TAKE A LOAN | User should be taken to the list of loan options after clicking on TAKE A LOAN | As Expected | P
4 |  |  | Verify user is able to click on PayDay Loan from the List of Loans available "provided the customer is NOT pre-qualified for a payday Loan" | - Login to app - click on LOANS - click on TAKE A LOAN - Click on Pay Day Loan | User should be click on Pay day loan | As Expected | P
5 |  | LOAN CALCULATOR | Verify User can see Loan - Loan Amount - Duration Date (30 days) - Repayment Amount - Loan attracts the % monthly Interest rate. | - Enter Amount - Click on Proceed | User is redirected to Account Details Screen | As Expected | P
6 |  |  | Verify User can slide and click on Tenor between 0 to 30 Days | - Click on TAKE A LOAN - Click onPayDay Loan - Enter Amount - Slide left or right to pick Tenor | User should be able to pick tenor | As Expected | P
7 |  |  | Verify User should not be able to Proceed if enter Negative Amount | - Enter Amount - Click on Proceed | Amount cannot be Negative | As Expected | P
8 |  |  | Verify User is not able to Proceed if the Tenor Day selected is ZERO (0) | - Click on TAKE A LOAN - Click on PayDay Loan - Enter Amount - Click and slide on tenor is 0 | Repayment tenor can not be Zero (0) | As Expected | P
9 |  |  | Verify User should not proceed if Enter ZERO (0) amount | - Click on TAKE A LOAN - Click on PayDay Loan - Enter Zero (0) Amount | User should be prompted to Enter Amount | As Expected | P
10 |  |  | Verify user is able to validate Estimated amount | - Click on TAKE A LOAN - Click on PayDay Loan - Enter Amount - Slide left or right to pick Tenor | Repayment amount should be calculated correctly | As Expected | P
11 |  |  | Verify the loan calculated the right amount of Estimated payment if the Amount is Altered | - Click on TAKE A LOAN - Click on PayDay Loan - Enter Amount - Slide left or right to pick Tenor - Alter Amount Entered | Repayment amount should be calculated correctly | As Expected | P
12 |  |  | Verify User can click on check Box to "I agree with Loans Terms and Conditions." | - Click on Proceed | User is redirected to Loan DashBoard | As Expected | P
13 |  | ACCOUNT DETAILS WEMA ACCOUNT | Verify user can select Account Type - Select account to debit - Check Box to "I agree that the information provided above should be used to request for my account statement." | Click on Proceed Button Click on Confirm Button to perform action | User is redirected to Score Card Result Screen | As Expected | P
14 |  | ACCOUNT DETAILS OTHER BANK ACCOUNT | Verify user can enter the following details - Enter Account Number - Select Bank Option from list - Check Box of details provided | Click on Proceed Button Click on Confirm Button to perform action | User is redirected to Document Upload | As Expected | P
15 |  | DOCUMENT UPLOAD PAGE | Verify User is able to upload Bank account statement | - Click on Upload Button - Upload statement | Statement is uploaded successful "Your statement has been successfully uploaded and will be reviewed within 24 hours. You will see your progress status on your dashboard" | As Expected | P
16 |  |  | Verify User is able to click on Continue button | - Click on Continue Button | User is redirected to Loan Dashboard | As Expected | P
17 |  | SOCRE CARD RESULT MY OTHER BANK | Verify user is able to see " Hi John Congratulations!!! Your loan has been granted. View details below." | - Click on Proceed on Loan DashBoard | Text is visible | As Expected | P
18 |  |  | Verify user is able to see Loan Amount Tenor (months) Monthly Repayment | - Click on Proceed on Loan DashBoard | Text is visible | As Expected | P
19 |  |  | Verify Accept Button is clickable | - Click on Accept Button- | User is redirected to Terms Page | As Expected | P
20 |  |  | Verify Decline Button is clickable | - Click on Decline Button - Click on Proceed to reject the loan | Loan is terminated | As Expected | P
21 | [5 empty] | As Expected | P
22 |  | SCORE CARD WEMA | Verify that user see the following details Text: Hi John Congratulations!!! Your loan has been granted. View details below Score Card Result Amount offered Due Date Repayment Amount "please note that 1.5% of the approved loan amount will be charged as management and insurance fee. | Click on Accept Button to proceed to Terms and conditions Click on Decline to Cancel Loan process | User is redirected to Terms and Conditions Page | As Expected | P
23 |  | TERMS | Verify that User can see TERMS & CONDITIONS (Payday Loan) Check Box to "I agree with Loans Terms & Conditions." | Click on Proceed Button | User is redirected to DashBoard | As Expected | P
24 |  | DISBURSEMENT | Verify that Loan is disbursed and account Credited with Loan Amount | Click on Home Button Click on Transaction History to confirm VAT, management & insurance fee is charged | Loan Amount is credited VAT, management & Insurance fee is charged accordingly. | As Expected | P
25 |  |  | Verify that User is notified by SMS and Mail on status, credit and debit of Loan | Check sms is received on debit of charges Check sms is received on credit of loan amount | SMS is received | As Expected | P
26 |  | LIQUIDATION | Verify User can Liquidate a Payday Loan Amount | Click on Loans Button Swipe on Current Loan and select loan Click on Pay Off Loan Click on YES button to confirm | User is redirected to Loan Repayment | As Expected | P
27 |  |  | Verify User can see outstanding loan balance, accumulated Interest to be deducted | Select Account to Debit Enter ALAT PIN Click on PAY LOAN Button | User is displayed with a message "Your pay day loan was successfully paid off" | As Expected | P
28 |  |  | Verify that User is notified by SMS and Mail on status, debit of Loan | Check sms and mail is received on debit of loan amount | SMS and Mail is received accordingly | As Expected | P
|  | INTEREST RATE REFACTOR | Verify Applicable Interest rate is display if User's account is domiciled with Wema bank and the tenor is 30 days (a month) on the loan calculator page | - Click on TAKE A LOAN - Click on Pay Day Loan - Select from dropdown and select Yes to indicate Customer is Wema bank domiciled - Enter Amount | User should be able to get the applicable interest rate of 2.08%pm i.e @25%p.a | As Expected | P
|  |  | Verify User's cannot select tenor less than 30 days on the loan calculator page | - Slide left or right to pick Tenor lesser than 30 days | User should be able to get the applicable interest rate of 2.08%pm i.e @25%p.a | As Expected | P
|  |  | Verify Applicable Interest rate is display if User's account is not domiciled with Wema bank and the tenor is 30 days on the loan calculator page | - Click on TAKE A LOAN - Click on Pay Day Loan - Select from dropdown and select NO to indicate Customer is Other bank domiciled - Enter Amount | User should be able to get the applicable interest rate of 2.17%pm i.e @26%p.a | As Expected | P
|  |  | Verify User's cannot select tenor less than 30 days on the loan calculator page | - Slide left or right to pick Tenor lesser than 30 days | User should be able to get the applicable interest rate of 2.17%pm i.e @26%p.a | As Expected | P
|  |  | Verify the Amount Entered is not less than 5,000 and not greater tha 500,000 | - Click on TAKE A LOAN - Click on Pay Day Loan - Enter Amount (5,000≥amount≤500,000) | Minimum Amount is 5,000 and Maximum is 500,000 | As Expected | P
|  |  | Verify debit account page is projected as WEMA if domicile account is Wema bank | - Click on TAKE A LOAN - Click on Pay Day Loan - Select from dropdown and select Yes to indicate Customer is Wema bank domiciled - Enter Amount - Click on Proceed | User debit account should project Wema bank | As Expected | P
|  |  | Verify debit account page is projected as Other Bank if domicile account is NOT Wema bank | - Click on TAKE A LOAN - Click on Pay Day Loan - Select from dropdownand select No to indicate Customer is Other bank domiciled - Enter Amount - Click on Proceed | User debit account should project Other bank | As Expected | P
|  |  | Verify Estimated amount changed when User's alter the amount on the loan calculation page | - Click on TAKE A LOAN - Click on Pay Day Loan - Select from dropdown by select NO to indicate Customer is Other bank domiciled - Enter Amount - Alter the initial amount | Estimated Amount should be in accordance of the Amount entered | As Expected | P
|  |  | Verify user should not be able to Proceed if no Tenor is selected | - Click on TAKE A LOAN - Click on Pay Day Loan - Select from dropdown by select NO to indicate Customer is Other bank domiciled - Enter Amount - Click on Proceed | User should not be able to Proceed if no tenor (Month) is selected | As Expected | P
|  |  | Verify user is able to slide between different accounts if he has more than one account saved on the profile | - Select Account to Debit from list of Accounts | User should be able to slide between accounts "On what account do you want this loan to be charged" | As Expected | P
|  |  | Ensure the API fetch statement from Finacle if account is Wema bank | - Click on TAKE A LOAN - Click on Pay Day Loan - Click dropdown to select Yes - Enter Amount - Click on Proceed | APIs should fecth the internal customer from Finacle | As Expected | P
|  |  | Ensure the statement from Finacle is converted to PDF irrespective of the later format and send to backoffice for review | - Click on TAKE A LOAN - Click on Pay Day Loan - Click dropdown to select Yes - Enter Amount - Click on Proceed | The statement of account get from Finacle should be converted to PDF and send to the backoffice for review and User's should get a message Loan application successful, your bank statement is being review. Kindly check back within 24hours | As Expected | P
|  | myBankStatement | Verify User is able to select Other bank from the loan page | - Click on TAKE A LOAN - Click on Pay Day Loan - Click the dropdown to select No | User should see "Is your account with wema bank" and NO | As Expected | P
|  |  | Verify user is able to select bank from the list of bank with the drop down arrow | - Click on TAKE A LOAN - Click on Pay Day Loan - Click the dropdown to select No - Enter Amount - Click on Proceed - Click and select bank from list of banks | User's should be able to select bank from the list of bank | As Expected | P
|  |  | Verify user is able to enter valid account number | - Enter valid account number | User's should be able to enter valid account number | As Expected | P
|  |  | Verify user cannot proceed if entered wrong account number | - Enter invalid account number | User should get an error message "we observed a BVN mismatch, please input the correct account details" | As Expected | P
|  |  | Verify if user is able to enter valid phone number linked to the BVN/account | - Enter valid phone number | User's should be able to enter valid phone number | As Expected | P
|  |  | Verify if user can proceed if inputed the wrong phone number | - Enter wrong phone number | User should be able to see projected masked phone number request, to complete for validation | As Expected | P
|  |  | Verify user is able to enter valid alat pin | - Enter valid pin | User's should be enter valid pin and proceed | As Expected | P
|  |  | Verify if user could proceed if entered invalid PIN | - Enter Invalid pin | User should get an error message "You have inputted an invalid pin" | As Expected | P
|  |  | Verify the number of trial is subject to 3 for entering invalid pin . | - Enter Invalid pin twice | User's should get the message of trial remaning | As Expected | p
|  |  | Verify the loan process terminate automatically subject to entering invalid pin thrice | - Enter invalid pin thrice | User should get an error message "Loan process terminated due to wrong pin" | As Expected | P
|  |  | Verify user tick the consent box permitting access to my bank statement with other banks to determine my income eligibility. | - Click on Check Box | Check Box is Clicked successfully | As Expected | P
|  |  | Verify if User can click on Proceed Button with right acoount number, phone number and pin | - Enter valid account number, phone number and pin - Click on Proceed Button - Click on proceed | User should be able to proceed | As Expected | P
|  |  | Verify user cannot proceed if the consent box is not tick | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on proceed | User should not be able to proceed | As Expected | P
|  |  | Ensure NIP's endpoint was queried to get customer name enquiry and BVN | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on proceed | APIs should queried NIP's endpoint to get customer name enquiry and BVN | As Expected | P
|  |  | Ensure the BVN number returned is validated and matches with the customer BVN on Wema Bank DB | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on proceed | API's validate the fetched customer details from NIP's if matches with the Wema Bank DB | As Expected | P
|  |  | Ensure the CSWF API was called from my bank statement to get the customer statement of account to conclude the process | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on proceed | APIs should fetch account statement of the account frommyBankStatement and send to the backoffice for review. and User's should be notified. | As Expected
|  | eSTATEMENT VERIFICATION PAGE | Verify User see progress message after click on proceed with valid data input | - Click on Proceed Button - Click on proceed to confirm that the input is correct | User should be able to see "We are currently fetching your statement of account, please give us a minute" | As Expected | P
|  |  | Verify if user get a response message after eSTATEMENT was generated successfully | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on Check Box - Click on proceed | The statement of account get from Finacle should be converted to PDF and send to the backoffice for review and User's should get a message "Loan application successful, your bank statement is being review. Kindly check back within 24hours" | As Expected
|  |  | Verify if user was directed to the loan dashboard after successful statement upload from finacle or any 3rd party service and converted to PDF | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on Check Box - Click on proceed | User should be able to get the message "Your statement has been uploaded and will be reviewed within 24hours". | As Expected
|  |  | Ensure customer loan was rejected if getting statement from finacle or any 3rd party fails | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on Check Box - Click on proceed | User should be able to get the message "Your request was declined because we are unable to validate your statement of account details due to service downtime, please try again later." | As Expected
|  |  | Ensure customer loan was rejected if getting statement from finacle or any 3rd party fails due to unavailability of required data | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on Check Box - Click on proceed | User should be able to get the message "Your request was declined because we are unable to get your statement of account details, please visit the nearest branch for more loan options" | As Expected
|  |  | Ensure existing parameters that apply is still maintain for the statement upload | - Login to the app - Click on Loan - Proceed with existing loan | User should be able to continue with the existing loan process if statement review was successful | As Expected

## Device Loan
Web Test Summary
[6 empty] | Pass (P) | 28 | 100%
Created by |  | MUMIN OLABIYI |  |  |  | Fail (F) | 0 | 0%
Reviewed by |  | MICHAEL ADINEBO |  |  |  | Not Executed (NE) | 0 | 0%
Date | [5 empty] | Total | 28 | 100%
TC NO | TC ID | Test Title | Test Scenario | Test Execution Steps | Expected Result | Actual Result | Status | Comments | Date Tested | Tester | Developer
1 |  | LOAN DASHBOARD | Verify user is able to login to the app | - Login to app with valid credentials | User should get logged in successfully | As Expected | P
2 |  |  | Verify user is able to click on LOANS in the menu on the bottom | - Login to App - Click on Loans Tab | User should be taken to the loan dashboard | As Expected | P
3 |  |  | Verify user is able to click on TAKE A LOAN on the loan dashboard | - Login to app - click on LOANS - click on TAKE A LOAN | User should be taken to the list of loan options after clicking on TAKE A LOAN | As Expected | P
4 |  |  | Verify user is able to click on DEVICE LOANS in the options and is taken to the loan details page | - Login to app - click on LOANS - click on TAKE A LOAN - click on DEVICE LOAN | User should be taken to the Device Loan page after clicking on button | As Expected | P
5 |  | LOAN CALCULATOR | Verify User can see "Please note that you are expected to pay a minimum of 20% of the total amount of your selected device to get a loan" | Statement is visible on top screen | Statement is visible on top screen | As Expected | P
|  |  | Verify User should not be able apply for loan more than 600,000 and with a minimum of 5000 | - Login to app - click on LOANS - click on TAKE A LOAN - click on DEVICE LOAN | User should not be able to select device which the 20% of it is more than 600,000 and less than 5,000 | As Expected | P
6 |  |  | Verify Loan Calculator is visible on the Device Loan Page | - Click on TAKE A LOAN - Click on Device loan | Loan Calculator is visible | As Expected | P
7 |  |  | Verify user is able to Select Vendor | - Click on TAKE A LOAN - Click on Device Loan - Click the drop down arrow to select Yes or No - Select Vendor from drop down list | Vendor is selected successfully | As Expected | P
8 |  |  | Verify User can selecct Product Category from list - Phone and Computer Accessories - Android Phones - Windows and Apple Laptops - Apple iPhones | - Click on Product Category from drop down list | Product Category is selected successfully | As Expected | P
9 |  |  | Verify user is able select Device | - Click on Device from drop down list | Device is selected successfully | As Expected | P
10 |  |  | Verify user is able view details of Device | - Click on View details | Device Information is displayed | As Expected | P
11 |  |  | Enter equity Amount | - Available Amount is Editable | - Available Amount is Editable | As Expected | P
12 |  |  | Verify User should not be able to Proceed if enter Negative Amount | - Enter Negative Amount - Click on Proceed | Amount cannot be Negative | As Expected | p
13 |  |  | Verify User is not able to Proceed if the Tenor Day selected is ZERO (0) | - Click on TAKE A LOAN - Click on Device Loan - Click the drop down arrow to select Yes or No - Select Product Type - Select Device - Select Vendor from drop down list - Click and slide on tenor to be Zero (0) | Repayment tenor can not be Zero (0) | As Expected | P
14 |  |  | Verify User should not proceed if Enter ZERO (0) amount | - Enter Zero (0) Amount - Click on Proceed | User should be prompted to Enter Amount | As Expected | P
15 |  |  | Verify user can select tenor | - Click on Tenor slider | Tenor is selected between 1 to 6 month | As Expected | P
16 |  |  | Verify User can select Tenure less than 1 month and 6 month | - Click on TAKE A LOAN - Click on Device Loan - Click the drop down arrow to select Yes or No - Select Product Type - Select Device - Select Vendor from drop down list - Slide left or right to pick Tenor | Tenor is selected between 1 to 6 month | As Expected | P
17 |  |  | Verify Estimated Monthly repayment is displayed | - Confirm that Estimated Monthly Repayment is displayed - Click on Proceed | Estimated monthly repayment and applicable interest rate should be seen - User is redirected to Account Details | As Expected | P
18 |  |  | Verify user is able to validate Estimated amount | - Click on TAKE A LOAN - Click on Device Loan - Click the drop down arrow to select Yes or No - Select Vendor from drop down list - Select Product Type - Select Device - Slide left or right to pick Tenor | Repayment amount should be calculated correctly | As Expected | P
19 |  |  | Verify the loan calculated the right amount of Estimated payment if the Amount is Altered | - Click on TAKE A LOAN - Click on Device Loan - Select Vendor from drop down list - Select Product Type - Select Device - Enter Amount - Slide left or right to pick Tenor - Alter Amount Entered | Repayment amount should be calculated correctly | As Expected | P
20 |  | ACCOUNT DETAILS WEMA ACCOUNT | Verify user can select Account Type - Select account to debit - Check Box to "I agree that the information provided above should be used to request for my account statement." | Click on Proceed Button Click on Confirm Button to perform action | User is redirected to Score Card Result Screen Loan Offer is displayed | As Expected | P
21 |  | LOAN RESULT WEMA | Verify that user see the following details Text: Hi John Congratulations!!! Your loan has been granted. View details below Device Loan Details Device Loan requested Loan offered Initial Payment Loan Tenor Monthly Repayment | Click on Accept Button to proceed to Terms and conditions Click on Decline to Cancel Loan process | User is redirected to Terms and Conditions Page | As Expected | P
22 |  | TERMS | Verify that User can see TERMS & CONDITIONS Check Box to "I agree with Loans Terms & Conditions." | Click on Proceed Button | User is redirected to Delivery Details | As Expected | P
23 |  | DELIVERY DETAILS Store Pick Up | Verify Vendor Phone Number and Reference Id is visible | Check Page to confirm | Vendor phone number and Reference Id is displayed | As Expected | P
24 |  |  | Verify User can select preferred store location from drop down list | Select Store from drop dwon list - Click on Proceed | User is redirected to Initial Payment | As Expected | P
25 |  | DELIVERY DETAILS Home Delivery | Verify User can fill the following details Enter Home Address, select State from drop dwon list, Enter City, Enter Phone number Confirm Delivery charge amount | Details are filled accordingly | User is redirected to Initial Payment | As Expected | P
26 |  | INITIAL PAYMENT | Verify user can see the following details Initial Payment Amount Delivery Cost Total Amount | Confirm details are populated with valid data | Details are populated | As Expected | P
27 |  |  | Verify User can select account to debit | Swipe to the right to select Account to debit | Account to debit is selected accordingly | As Expected | P
28 |  |  | Verify User can enter ALAT PIN | Enter valid ALAT PIN Click on PAY Button | ALAT PIN is valid User is redirected to Loan DashBoard and account is debit with Available amount | As Expected | P
|  | INTEREST RATE REFACTOR | Verify Applicable Interest rate is display if User's account is domiciled with Wema bank and the tenor is 6 months on the loan calculator page | - Click on TAKE A LOAN - Click on Device Loan - Click the drop down arrow to select Yes or No - Select Vendor from drop down list - Select Product Type - Select Device - Enter Amount - Slide left or right to pick Tenor = 6 | User should be able to get the applicable interest rate of 2.08%pm i.e @25%p.a | As Expected | P
|  |  | Verify Applicable Interest rate is display if User's account is domiciled with Wema bank and the tenor is less than 6 months on the calculator page | - Click on TAKE A LOAN - Click on Device Loan - Select from dropdown and select Yes to indicate Customer is Wema bank domiciled - Select Vendor from drop down list - Select Product Type - Select Device - Enter Amount - Slide left or right to pick Tenor lesser than 6 Months | User should be able to get the applicable interest rate of 2.08%pm i.e @25%p.a | As Expected | P
|  |  | Verify if user's account is domicile with Wema bank and can select more than 6 months on the loan calculator page | - Click on TAKE A LOAN - Click on Device Loan - Select from dropdown and select Yes to indicate Customer is Wema bank domiciled - Select Vendor from drop down list - Select Product Type - Select Device - Enter Amount - Slide left or right to pick Tenor greater than 6 Months | User should not be able to select more than 6 months on the loan calculator page | As Expected | P
|  |  | Verify Applicable Interest rate is display if User's account is not domiciled with Wema bank and the tenor is 6 months on the loan calculator page | - Click on TAKE A LOAN - Click on Device Loan - Select from dropdown and select No to indicate Customer is not Wema bank domiciled - Select Vendor from drop down list - Select Product Type - Select Device - Enter Amount - Slide left or right to pick Tenor = 6 | User should be able to get the applicable interest rate of 2.17%pm i.e @26%p.a | As Expected | P
|  |  | Verify Applicable Interest rate is display if User's account is not domiciled with Wema bank and the tenor is less than 6 months on the loan calculator page | - Click on TAKE A LOAN - Click on Device Loan - Select from dropdown and select No to indicate Customer is not Wema bank domiciled - Select Vendor from drop down list - Select Product Type - Select Device - Enter Amount - Slide left or right to pick Tenor lesser than 6 Months | User should be able to get the applicable interest rate of 2.17%pm i.e @26%p.a | As Expected | P
|  |  | Verify if user's account is not domicile with Wema bank and can select more than 6 months on the loan calculator page | - Click on TAKE A LOAN - Click on Salary Based Loan - Select from dropdown to indicate Customer is Other bank domiciled - Enter Amount - Slide left or right to pick Tenor 6 Months greater | User should not be able to 6 months select more than on the loan calculator page | As Expected | P
|  |  | Verify Applicable Interest rate is changed when User's alter the option of account from Wema bank to other bank and the tenor is 6 month on the loan calculator page, | - Select from dropdown and select NO Customer is Other bank domiciled | User should be able to get the applicable interest rate 2.17%pm i.e @26%p.a | As Expected | P
|  |  | Verify Applicable Interest rate is changed when User's alter the option of account from other bank to Wema Bank and the tenor is less than 6 month on the loan calculator page, | - Select from dropdown and select NO Customer is Other bank domiciled | User should be able to get the applicable interest rate of 2.08%pm i.e @25%p.a | As Expected | P
|  |  | Verify debit account page is projected as WEMA if domicile account is Wema bank | - Select from dropdown to select Yes Customer is Wema bank domiciled - Enter Amount - Slide left or right to pick Tenor - Click on Proceed | User debit account should project Wema bank | As Expected | P
|  |  | Verify debit account page is projected as Other Bank if domicile account is NOT Wema bank | - Select from dropdown to select NO Customer is not Wema bank domiciled - Enter Amount - Slide left or right to pick Tenor - Click on Proceed | User debit account should project Other bank | As Expected | P
|  |  | Verify Estimated amount changed when User's alter the minimum amount on the loan calculation page | - Slide left or right to pick Tenor - Alter the initial amount | Estimated Amount should be in accordance of the Amount entered | As Expected | P
|  |  | Verify user should not be able to Proceed if no Tenor is selected | - Click on TAKE A LOAN - Click on Salary Based Loan - Select from dropdown by select NO to indicate Customer is Other bank domiciled - Enter Amount - Click on Proceed | User should not be able to Proceed if no tenor (Month) is selected | As Expected | P
|  |  | Verify user is able to slide between different accounts if he has more than one account saved on the profile | - Select Account to Debit from list of Accounts | User should be able to slide between accounts "On what account do you want this loan to be charged" | As Expected | P
|  |  | Ensure the API fetch statement from Finacle if account is Wema bank | - Click on TAKE A LOAN - Click on Device Loan - Select from dropdown and select Yes to indicate Customer is Wema bank domiciled - Select Vendor from drop down list - Select Product Type - Select Device - Slide left or right to pick Tenor - Click on Proceed | APIs should fecth the internal customer from Finacle | As Expected | P
|  |  | Ensure the statement from Finacle is converted to PDF irrespective of the later format and send to backoffice for review | - Click on TAKE A LOAN - Click on Device Loan - Select from dropdown and select Yes to indicate Customer is Wema bank domiciled - Select Vendor from drop down list - Select Product Type - Select Device - Slide left or right to pick Tenor - Click on Proceed | The statement of account get from Finacle should be converted to PDF and send to the backoffice for review and User's should get a message Loan application successful, your bank statement is being review. Kindly check back within 24hours
|  | myBankStatement | Verify User is able to select Other bank from the loan page | - Click on TAKE A LOAN - Click on DeviceLoan - Click the dropdown to select No | User should see "Is your account with wema bank" and NO | As Expected | P
|  |  | Verify user is able to select bank from the list of bank with the drop down arrow | - Click on TAKE A LOAN - Click on Device Loan - Click the dropdown to select No - Select Vendor from drop down list - Select Product Type - Select Device - Slide left or right to pick Tenor - Click on Proceed - Click and select bank from list of banks | User's should be able to select bank from the list of bank | As Expected | P
|  |  | Verify user is able to enter valid account number | - Enter valid account number | User's should be able to enter valid account number | As Expected | P
|  |  | Verify user cannot proceed if entered wrong account number | - Enter invalid account number | User should get an error message "we observed a BVN mismatch, please input the correct account details" | As Expected | P
|  |  | Verify if user is able to enter valid phone number linked to the BVN/account | - Enter valid phone number | User's should be able to enter valid phone number | As Expected | P
|  |  | Verify if user can proceed if inputed the wrong phone number | - Enter wrong phone number | User should be able to see projected masked phone number request, to complete for validation | As Expected | P
|  |  | Verify user is able to enter valid alat pin | - Enter valid pin | User's should be enter valid pin and proceed | As Expected | P
|  |  | Verify if user could proceed if entered invalid PIN | - Enter Invalid pin | User should get an error message "You have inputted an invalid pin" | As Expected | P
|  |  | Verify the number of trial is subject to 3 for entering invalid pin . | - Enter Invalid pin twice | User's should get the message of trial remaning | As Expected | P
|  |  | Verify the loan process terminate automatically subject to entering invalid pin thrice | - Enter invalid pin thrice | User should get an error message "Loan process terminated due to wrong pin" | As Expected | p
|  |  | Verify user tick the consent box permitting access to my bank statement with other banks to determine my income eligibility. | - Click on Check Box | Check Box is Clicked successfully | As Expected | P
|  |  | Verify if User can click on Proceed Button with right acoount number, phone number and pin | - Enter valid account number, phone number and pin - Click on Proceed Button - Click on proceed | User should be able to proceed | As Expected | P
|  |  | Verify user cannot proceed if the consent box is not tick | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on proceed | User should not be able to proceed | As Expected | P
|  |  | Ensure NIP's endpoint was queried to get customer name enquiry and BVN | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on proceed | APIs should queried NIP's endpoint to get customer name enquiry and BVN | As Expected | P
|  |  | Ensure the BVN number returned is validated and matches with the customer BVN on Wema Bank DB | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on proceed | API's validate the fetched customer details from NIP's if matches with the Wema Bank DB | As Expected | P
|  |  | Ensure the CSWF API was called from my bank statement to get the customer statement of account to conclude the process | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on proceed | APIs should fetch account statement of the account frommyBankStatement and send to the backoffice for review. and User's should be notified. | As Expected | P
|  | eSTATEMENT VERIFICATION PAGE | Verify User see progress message after click on proceed with valid data input | - Click on Proceed Button - Click on proceed to confirm that the input is correct | User should be able to see "We are currently fetching your statement of account, please give us a minute" | As Expected | P
|  |  | Verify if user get a response message after eSTATEMENT was generated successfully | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on Check Box - Click on proceed | The statement of account get from Finacle should be converted to PDF and send to the backoffice for review and User's should get a message "Loan application successful, your bank statement is being review. Kindly check back within 24hours" | As Expected | P
|  |  | Verify if user was directed to the loan dashboard after successful statement upload from finacle or any 3rd party service and converted to PDF | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on Check Box - Click on proceed | User should be able to get the message "Your statement has been uploaded and will be reviewed within 24hours". | As Expected | P
|  |  | Ensure customer loan was rejected if getting statement from finacle or any 3rd party fails | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on Check Box - Click on proceed | User should be able to get the message "Your request was declined because we are unable to validate your statement of account details due to service downtime, please try again later." | As Expected | P
|  |  | Ensure customer loan was rejected if getting statement from finacle or any 3rd party fails due to unavailability of required data | - Click drop down List and select bank option - Enter valid account number - Enter valid phone number - Enter valid pin - Click on Check Box - Click on proceed | User should be able to get the message "Your request was declined because we are unable to get your statement of account details, please visit the nearest branch for more loan options" | As Expected | P
|  |  | Ensure existing parameters that apply is still maintain for the statement upload | - Login to the app - Click on Loan - Proceed with existing loan | User should be able to continue with the existing loan process if statement review was successful | As Expected | P

## Goal
Test Summary
[6 empty] | Pass (P) | 20 | 100%
Created by |  | MUMIN OLABIYI |  |  |  | Fail (F) | 0 | 0%
Reviewed by |  | MICHAEL ADINEBO |  |  |  | Not Executed (NE) | 0 | 0%
Date | [5 empty] | Total | 20 | 100%
TC NO | TC ID | Test Title | Test Scenario | Test Execution Steps | Expected Result | Actual Result | Status | Comments | Date Tested | Tester | Developer
1 |  |  | Verify user is able to login to the app | - Login to app with valid credentials | User should get logged in successfully | As Expected | P
2 |  |  | Verify user is able to click on LOANS in the menu on the bottom | - Login to app - Click on Loans Tab | User should be taken to the loan dashboard | As Expected | P
3 |  |  | Verify user is able to click on TAKE A LOAN on the loan dashboard | - Login to app - click on LOANS - click on TAKE A LOAN | User should be taken to the list of loan options after clicking on TAKE A LOAN | As Expected | P
4 |  |  | Verify user is able to click on GOAL BASED LOANS in the options and is taken to the loan details page | - Login to app - click on LOANS - click on TAKE A LOAN - click on GOAL BASED LOANS | User should be taken to the Goal Based Loan page after clicking on button | As Expected | P
5 |  | LOAN REQUEST INITIATION - EXISTING CUSTOMER | Verify user is able to view the loan type dropdown and select preferred loan | - click on LOANS - click on TAKE A LOAN - click on GOAL BASED LOAN | User should be able to select Goal Based Lending option | As Expected | P
6 |  |  | Verify loan available is only 80% of Goal | - Click on TAKE A LOAN - Click on Goal Based Loan | Loan Calculator is visible | As Expected | P
|  |  | Verify Goal loan is available for only User that set a goal | - Click on TAKE A LOAN - Click on Goal Based Loan | Only availabe for User that set Goal | As Expected | P
7 |  |  | Verify user is able to Enter loan Amount | - Click on TAKE A LOAN - Click on Goal Based Loan - Enter Amount | User should be able to enter a valid Amount | As Expected | P
8 |  |  | Verify User can select Account to CREDIT | - Click on TAKE A LOAN - Click on Goal Based Loan - Enter Loan Amount - Swipe on Account to Credit | Account is selected | As Expected | P
9 |  |  | Verify user is able not able to proceed if loan amount is negative | - Click on TAKE A LOAN - Click on Goal Based Loan - Enter Negative Amount | Loan amount cannot be negative value | As Expected | P
10 |  |  | Verify user is able not able to proceed if loan amount is ZERO | - Click on TAKE A LOAN - Click on Goal Based Loan - Enter ZERO Amount | Loan amount cannot be zero | As Expected | P
11 |  |  | Verify user is able to validate Estimated amount | - Click on TAKE A LOAN - Click on Goal Based Loan - Enter Amount - Slide left or right to pick Tenor | Repayment amount should be calculated correctly | As Expected | P
12 |  |  | Verify the loan calculated the right amount of Estimated payment if the Amount is Altered | - Click on TAKE A LOAN - Click on Goal Based Loan - Enter Amount - Slide left or right to pick Tenor - Alter Amount Entered | Repayment amount should be calculated correctly | As Expected | P
13 |  |  | Verify User can Apply for Loan | - Click on TAKE A LOAN - Click on Goal Based Loan - Enter Loan Amount - Enter ALAT PIN - Click on GET LOAN | Terms and Condition Screen is displayed | As Expected | P
14 |  |  | Verify LoanTerms and Condition is visible | - Click on TAKE A LOAN - Click on Goal Based Loan - Enter Loan Amount - Enter ALAT PIN - Click on GET LOAN - Click on Check Box - Click on Proceed | Loan is disbursed successful | As Expected | P
15 |  | DISBURSEMENT | Verify that Loan is disbursed and account Credited with Loan Amount | Click on Home Button Click on Transaction History to confirm Credit | Loan Amount is credited | As Expected | P
16 |  |  | Verify that User is notified by SMS and Mail on status, credit and debit of Loan | Check sms is received on credit of loan amount | SMS is received | As Expected | P
17 |  | LIQUIDATION | Verify User can perform a fully Liquidate a Goal Loan Amount | Click on Loans Button Swipe on Current Loan and select loan Click on Pay Off Loan Click on Full Liquidation Click on YES button to confirm | User is redirected to Loan Repayment | As Expected | P
18 |  |  | Verify User can perform a Part - Liquidate a Goal Loan Amount | Click on Loans Button Swipe on Current Loan and select loan Click on Pay Off Loan Click on Part - Liquidation Enter Amount Click on YES button to confirm | User is redirected to Loan Repayment | As Expected | P
19 |  |  | Verify User can see outstanding loan balance, accumulated Interest to be deducted | Select Account to Debit Enter ALAT PIN Click on PAY LOAN Button | User is displayed with a message "Your Goal loan was successfully paid off" | As Expected | P
20 |  |  | Verify that User is notified by SMS and Mail on status, debit of Loan | Check sms and mail is received on debit of loan amount | SMS and Mail is received accordingly | As Expected | P